## Full 1
| PROJECT TITLE | Analysis of the effect of PMM2 variants on PMM2-CDG | [5 empty] | COMPANY NAME |  | UPC
| PROJECT MEMBERS | Adriana Dotsenko, Dàlia Jordan, Salomé Murillo, Elsa Rosado i Noah Quixal | [5 empty] | DATE |  | 2026-10-08
ID | TASK TITLE | TASK OWNER | PLANNED START DATE | PLANNED END DATE | REAL START DATE | REAL END DATE | DURATION (days) | STATUS OF THE TASK | W40 |  | W41 |  |  |  |  | W42 |  |  |  | W43 |  |  |  |  | W44 |  |  |  |  | W45 |  |  |  | OUTPUT / ACCOMPLISHED WHEN
[9 empty] | 01/10 T | 02/10 F | 05/10 M | 06/10 T | 07/10 W | 08/10 T | 09/10 F | 13/10 T | 14/10 W | 15/10 T | 16/10 F | 19/10 M | 20/10 T | 21/10 W | 22/10 T | 23/10 F | 26/10 M | 27/10 T | 28/10 W | 29/10 T | 30/10 F | 02/11 M | 03/11 T | 04/11 W | 05/11 T
WP1 | Planning and setup |  | 2026-09-17 | 2026-10-09 |  |  | 16
1.1 | Create the GitHub repository | Dàlia + Salomé | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 1 | Completed | [25 empty] | Output: Repository with folders, README and .gitignore (before grid: 17/09 is earlier than the 01/10 grid start)
1.2 | Kick-off meeting | All | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 1 | Completed | [25 empty] | Output: Organisation and brainstorming
1.3 | Build the Gantt chart | Dàlia + Noah | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | 2 | Completed | [25 empty] | Output: Complete Gantt chart
1.4 | Define objectives and team | Adriana | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | 2 | Completed | [25 empty] | Output: Objectives, roles and background written in the README
1.5 | Risk analysis | Elsa | 2026-10-02 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2 | Completed | [25 empty] | Output: Risk matrix and risk statements
1.6 | Status tracking document / upload the Gantt to Git | Dàlia + Noah | 2026-10-08 | 2026-10-09 | 2026-10-08 |  | 2 | Completed | [25 empty] | Output: Table in status/
1.7 | Review and submission | Dàlia | 2026-10-08 | 2026-10-09 |  |  | 2 | Completed | [25 empty] | Output: Upload to Moodle and update the Gantt
WP2 | Information gathering |  | 2026-10-01 | 2026-10-22 |  |  | 15
2.1 | Search for reviews | Salomé | 2026-10-01 | 2026-10-05 | 2026-10-02 | 2026-10-06 | 3 | Completed | [25 empty] | Output: At least 3 reviews
2.2 | Search for original papers on the mechanism | Salomé | 2026-10-01 | 2026-10-06 | 2026-10-05 | 2026-10-06 | 4 | Completed | [25 empty] | Output: At least 5 papers
2.3 | OMIM: gene-disease relationship | Adriana | 2026-10-06 | 2026-10-13 |  |  | 5 | Pending | [25 empty] | Output: Notes on the gene and the phenotype
2.4 | UniProt and choice of 2 species | Adriana | 2026-10-06 | 2026-10-13 | 2026-10-13 | 2026-10-13 | 5 | Completed | [25 empty] | Output: Protein entry and justification of the species
2.5 | InterPro: domains | Elsa | 2026-10-06 | 2026-10-13 |  |  | 5 | Pending | [25 empty] | Output: List of domains
2.6 | PDB: healthy and variant structure | Elsa | 2026-10-06 | 2026-10-13 |  |  | 5 | Completed | [25 empty] | Output: Selected PDB IDs
2.7 | Reference management | Salomé | 2026-10-01 | 2026-10-22 | 2026-10-15 |  | 15 | In progress | [25 empty] | Output: List in BMC format
WP3 | Bioinformatic analysis |  | 2026-10-13 | 2026-10-22 |  |  | 8
3.1 | Retrieve FASTA sequences (reference, variant and orthologs) | Dàlia | 2026-10-13 | 2026-10-15 |  |  | 3 | Completed | [25 empty] | Output: FASTA files
3.2 | Alignments and conservation | Dàlia | 2026-10-15 | 2026-10-19 | 2026-10-15 |  | 3 | In progress | [25 empty] | Output: Alignment and conservation table
3.3 | Structural comparison: healthy vs variant | Noah | 2026-10-13 | 2026-10-19 | 2026-10-15 |  | 5 | In progress | [25 empty] | Output: Images and notes
3.4 | Figures | Dàlia + Noah | 2026-10-20 | 2026-10-22 |  |  | 3 | Backlog | [25 empty] | Output: Figures in figures/
3.5 | Evolutionary and homolog interpretation | Noah | 2026-10-13 | 2026-10-19 | 2026-10-15 |  | 5 | In progress | [25 empty] | Output: Interpretation notes
3.6 | Limitations of each analysis | Adriana | 2026-10-20 | 2026-10-22 |  |  | 3 | Backlog | [25 empty] | Output: Limitations summary (to be integrated into the Discussion section)
WP4 | Report |  | 2026-10-16 | 2026-10-26 |  |  | 7
4.1 | Cross-explanation session | All | 2026-10-20 | 2026-10-20 |  |  | 1 | Backlog
4.2 | Report outline | Salomé | 2026-10-16 | 2026-10-16 |  |  | 1 | Backlog | [25 empty] | Output: Report outline (.md file with the BMC sections)
4.3 | Introduction | Salomé | 2026-10-19 | 2026-10-22 |  |  | 4 | Backlog
4.4 | Methods | Noah | 2026-10-20 | 2026-10-22 |  |  | 3 | Backlog
4.5 | Results | Dàlia | 2026-10-20 | 2026-10-22 |  |  | 3 | Backlog
4.6 | Discussion | Adriana | 2026-10-20 | 2026-10-22 |  |  | 3 | Backlog
4.7 | Abstract and author contributions | Elsa | 2026-10-22 | 2026-10-23 |  |  | 2 | Backlog
4.8 | Joint review | All | 2026-10-23 | 2026-10-23 |  |  | 1 | Backlog
4.9 | Submission on Moodle | Adriana | 2026-10-26 | 2026-10-26 |  |  | 1 | Backlog
WP5 | Defense |  | 2026-10-27 | 2026-11-05 |  |  | 8
5.1 | Slides | All | 2026-10-27 | 2026-10-29 |  |  | 3 | Backlog
5.2 | Formatting presentation | Elsa | 2026-10-30 | 2026-10-30 |  |  | 1 | Backlog
5.3 | Two rehearsals | All | 2026-11-03 | 2026-11-04 |  |  | 2 | Backlog
5.4 | Project defense | All | 2026-11-05 | 2026-11-05 |  |  | 1 | Backlog
TOTAL | Whole project |  | 2026-09-17 | 2026-11-05 |  |  | 34
Formulas:
DURATION (days) = NETWORKDAYS([PLANNED START DATE],[PLANNED END DATE],Holidays!$A2:A1000)

## Holidays
Holiday date
2026-09-11
2026-09-24
2026-10-12
2026-12-08